[ C ]   THE CORPORATE

| TO | Double Materiality Working Group, Executive Leadership Team |
| --- | --- |
| FROM | Sustainability Manager, The Corporate |
| DATE | 2 April 2026 |
| SUBJECT | Stakeholder Engagement Logic and Project Timeline Approval |

STAKEHOLDER ENGAGEMENT STRATEGY

Data Architecture,

Weighting Logic &

Project Timeline

Approved framework governing how materiality data is collected,

weighted, and delivered for The Corporate's 2025 ESG assessment.

APPROVED BY	STATUS

Double Materiality Working Group	Approved  |  2 April 2026

Executive Summary

The Double Materiality Working Group met to finalize the data collection architecture and project timeline for The Corporate's 2025 ESG assessment. To comply with evolving global reporting requirements, including CSRD readiness for the Wroclaw operations and supply chain diligence globally, the working group has approved a hybrid data architecture.

This approach pairs high-volume quantitative collection with high-leverage qualitative engagement to build an auditable, balanced materiality matrix.

Approved Stakeholder Engagement Framework

The working group finalized a bifurcated strategy. Generic automated surveys are not used for high-leverage external stakeholders. Anecdotal interviews are not used exclusively for the operational workforce. The architecture is structured as follows.

| APPROACH | STAKEHOLDER GROUP | SAMPLE SIZE & LOGISTICS | SCORING LOGIC / DATA PIPELINE |
| --- | --- | --- | --- |
| Quantitative | Employees | 1,000 completed surveys via randomized, stratified selection across all 5 global manufacturing facilities. | Stratified Mean Formula: Blended average weighted by facility headcount to prevent Shenzhen (4,500 workers) from statistically erasing smaller sites. |
| Quantitative | Suppliers | 50 key Tier-1 suppliers selected from an active database of 500+ vendors. | Risk & Spend Weighted Formula: Inputs from high-impact raw material providers (Lithium, Cobalt, Aluminum) carry higher mathematical weight due to Scope 3 disruption risk. |
| Qualitative | Investors | 5 in-depth interviews targeting top-tier institutional investors by asset size and holdings. | Scoring Decision Rubric: Transcripts translated into 1-5 coordinates using standardized operational and financial risk definitions. |
| Qualitative | Customers | 15 structured interviews with major global B2B OEMs across Europe, APAC, and the Americas. | Revenue-Impact Rubric: Feedback converted to numeric scores weighted against account revenue and future contract renewals. |

Key Alignment Note: Quantitative surveys provide statistical breadth to defend internal operational scores. Qualitative interviews provide the strategic depth required by the board. The clean divide protects data integrity.

Cross-Stakeholder Weighting Scheme

To produce a single blended score per topic across all 4 stakeholder groups, the working group approved equal-weight distribution. Each group contributes 25% of the final aggregated score on both the Financial Risk and Impact dimensions.

| STAKEHOLDER GROUP | WEIGHT |
| --- | --- |
| Employees | 25% |
| Suppliers | 25% |
| Investors | 25% |
| Customers | 25% |
| Total | 100% |

Rationale: Equal weighting ensures no single stakeholder perspective dominates. This approach is auditable, transparent, and defensible for CSRD reporting. Weighting may be revisited in future assessment cycles.

Formula applied to both axes independently:

Final Score = (Employee Score x 0.25) + (Supplier Score x 0.25) + (Investor Score x 0.25) + (Customer Score x 0.25)

Materiality Threshold Definitions

The following thresholds govern which topics are classified as material and require disclosure. Thresholds apply to final blended scores on a 1.0 to 5.0 scale across both axes.

Priority Rule: Classifications are evaluated top-down. The highest matching classification always applies. A strong score on one axis cannot be overridden by a weak score on the other.

| CLASSIFICATION | THRESHOLD CRITERIA | DISCLOSURE OBLIGATION |
| --- | --- | --- |
| Highly Material | 3.5 or above on BOTH Financial Risk AND Impact axes. | Mandatory disclosure with full narrative, targets, and performance data. |
| Material | 3.0 or above on EITHER Financial Risk OR Impact axis, and does not qualify as Highly Material. | Mandatory disclosure required. |
| Watch List | At least one axis scores 2.0-2.9, and neither axis reaches 3.0. | Monitored and documented. Not required for current reporting cycle. |
| Not Material | Both axes score below 2.0. | Excluded from disclosure scope. |

Worked example: A topic scoring 3.3 on Financial Risk and 2.5 on Impact is classified as Material. The Financial Risk axis clears the 3.0 threshold, which is sufficient. The 2.5 Impact score falls in the Watch List range but does not apply because the priority rule assigns the highest matching classification.

Approved Project Timeline & Milestones

The working group locked a strict 4-month roadmap to ensure final materiality scores are integrated into upcoming corporate strategy cycles.

| APRIL BLOCK | Launch. Distribute digital questionnaires to employee portals and supplier compliance tracks. Begin outreach and scheduling for 20 qualitative interview slots (Investors and Customers). |
| --- | --- |

| MAY BLOCK | Continuous Data Collection. All survey links active. Interviews conducted throughout April and May. Hard deadline for all stakeholder feedback: 31 May 2026. |
| --- | --- |

| JUNE BLOCK | Evaluation. Feedback window closes. Begin data cleansing, incomplete entry removal, and qualitative transcript coding against approved scoring rubrics. |
| --- | --- |

| JULY BLOCK | Statistical Analysis. Apply facility population weights and 25% equal cross-stakeholder weights to produce final blended coordinates per topic. |
| --- | --- |

| END OF JULY | Matrix Delivery. Final aggregated scores (1.0-5.0 coordinates on both axes) classified against materiality thresholds, signed off, and formatted for executive distribution. |
| --- | --- |

Next Steps & Immediate Actions

| RESPONSIBLE OWNER | ACTION REQUIRED |
| --- | --- |
| HR / Internal Comms | Prepare localized internal communications for the 5 manufacturing sites to optimize employee survey response rates. |
| Procurement / Supply Chain | Issue the supplier ESG assessment invitation to the targeted top-50 Tier-1 vendors. |
| Investor Relations | Initiate contact with the pre-selected 5 institutional investor groups to book structured interview slots. |
| Account Management | Initiate contact with the pre-selected 15 major OEM accounts to book structured interview slots. |

The Corporate  |  Stakeholder Engagement & Materiality Strategy  |  Approved 2 April 2026